## Simple Business Risk Register
SIMPLE BUSINESS RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
Map visualisation libraries resulting in configuration issues | Key design feature will be unavailable on both pages of the application | 5 | 2 | 10 | Check documentation before choosing a library | Front-end team | 1
Geoapify crashing or not working | Main app functionality won't work | 5 | 1 | 5 | Check documentation before using and regularly test API routes | Full-stack | 2
Pushing API Key to Github | Breach of security. API daily limits being reached and app temporarily being down. | 3 | 4 | 12 | Peer review code before pushing up to github and adding API key to .gitignore | Back-end team | 3
Technical difficulties related to wifi on demo day | Poor user experience on demo day | 4 | 5 | 20 | Make sure the person with bad wifi doesn't share their screen on demo day | Faiz (team member) | 4
Limited accessibility on app | App may be harder to scale and not practical for particular demographics | 3 | 3 | 9 | Use sematic HTML and conduct UX/UI research | Front-end team | 5
API limit reached due recursion | A high amount of credits being used a day beyond what is allowed by the free trial | 3 | 4 | 12 | Appropriately using states such as useEffect | Front-end team
Too many tabs open | Laptops slowing down and effecting the workflow | 3 | 5 | 15 | Close tabs down when they are not in use | Emmanuel

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.